## README
Last Update | 2018-10-17
Author | Jae Hyun Yim, Justin Yoo, Jang-Shing Lin, Jiawei Chen, Justin Li
Email | jyim008@ucr.edu, jyoo030@ucr.edu, jchen313@ucr.edu, lli109@ucr.edu, jlin065@ucr.edu
Description | Spotify website version (Modified version)
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Host rooms | As a user I want to create a room with a unique room ID that give to other users so they can join my room. I become the host. | 3 | 1 | Done
2 | Join rooms | I want to be able to use a unique room ID to join another users room. | 3 | 5 | Done
3 | Add to queue | As a host or user I want to be able to add songs to the queue. | 3 | 9 | Done
4 | Host controls | As a host, I want to be able add or remove songs from the queue, and play and skip. | 4 | 10 | Done
5 | Search Songs | As a host or user I want to be able to be able to search for songs using the Spotify API. | 4 | 8 | Done
6 | Spotify API | As the host of the room I want to be able to connect use my Spotify Premium Account | 8 | 2 | Done
7 | Close rooms | As a host when close the room manually or close the tab, I expect the room to close and to log me out of my Spotify account and kick out all the other users. | 3 | 3 | Done
8 | Song status | As a user I should be able to see current song playing, next songs, and the player. | 3 | 6 | next
9 | Repeat | As a user I should be able to repeat songs. | 2 | 13 | next
10 | Duplicates | As a host I should be able to decide if duplicates are added to the queue. | 2 | 12 | Testing/(frontend)
11 | Voting | As a user I should be able to vote on whether to remove/skip the current and next songs. | 3 | 11 | next
12 | Number of users | As a host or user I should be able to see number of users currently in the room | 2 | 7 | Testing/(frontend)
13 | Users Leaving | As a user when I close the tab or leave the room. The room should not close | 2 | 4 | Done
| Total |  | 42

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Create basic interface for the main page, with CreateRoom and JoinRoom button. (Enoch)
Task 2: CreateRoom button creates a new room page and displays song status (Justin Li, Jiawei Chen)
Task 3: The new room page is then connected to spotify account API. (Jae)
Task 4: Generate unique code for room access (Justin Y)
Task 5: Users can access the room page with the unique code. (Justin Yoo)
Task 6: a host or user is able to be able to search for songs using the Spotify API. (Justin yoo)
Task 7: a host or user is able to add songs to the queue. (Jae)
Task 8: a host is be able add or remove songs from the queue, and play and skip. (Jae)
Task 9: Reconcile React code with ejs/bootstrap (Enoch, Jiawei, Justin Li)
Task 10: a user should be able to see current song playing, next songs, and the player. (Backend)
Task 11: a user should be able to see current song playing, next songs, and the player. (Frontend) (Jiawei, Enoch)
Task 12: a host or user should be able to see number of users currently in the room(Justin Li, Enoch)
Task 13: As a user I should be able to repeat songs. (Justin Li, Jae)
Task 14: As a host I should be able to decide if duplicates are added to the queue. (Justin Li, Jae)
Task 15: As a user I should be able to vote on whether to remove/skip the current and next songs. (Justin Yoo, Jiawei)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Enoch | Task 1: Create basic interface for the main page, with CreateRoom and JoinRoom button. (Enoch)
1 |  | Task 2: CreateRoom button creates a new room page and displays song status (Justin Li, Jiawei Chen)
1 |  | Task 3: The new room page is then connected to spotify account API. (Jae)
1 |  | Task 4: Generate unique code for room access (Justin Y)
1 |  | Task 5: Users can access the room page with the unique code. (Justin Yoo)
2 | Jae | Task 6: a host or user is able to be able to search for songs using the Spotify API. (Justin yoo)
2 |  | Task 7: a host or user is able to add songs to the queue. (Jae)
2 |  | Task 8: a host is be able add or remove songs from the queue, and play and skip. (Jae)
2 |  | Task 9: Reconcile React code with ejs/bootstrap (Enoch, Jiawei, Justin Li)
2 |  | Task 10: a user should be able to see current song playing, next songs, and the player. (Backend)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 42 | 0 | 0 | 42 | 42
1 | 42 | 19 | 19 | 23 | 23
2 | 42 | 11 | 30 | 12 | 12
3 | 42